## Sheet1
Week | Objective
10/23 - 10/27 | Finalize block diagram with parts chosen
10/30 - 11/3
11/6 - 11/10
11/13 - 11/17
11/20 - 11/24
11/27 - 12/1 | Fully completed and integrated with TC
| Monday 10/23 | Tuesday 10/24 | Wednesday 10/25 | Thursday 10/26 | Friday 10/27
| cant do 2799 | Meet with Prof Bitar Confirm ISP | Finalize block diagram + component selection Begin schematic design (Will) Include 7-seg just in case |  | Finish schematic design Begin PCB design
Sunday | Monday 10/30 | Tuesday | Wed | Thurs | Friday
Rough PCB design finished | Begin teching STM32CUBEIDE to others. They start software dev |  | Order PCBs and parts by midnight | Software development | Software development
| Monday 11/6 | Tuesday | Wed | Thurs | Friday
| Software development | Software development | Software development | Software development | PCBs arrive
| Monday 11/13 | Tuesday | Wed | Thurs | Friday
| Monday 11/20 | Tuesday | Wed | Thurs | Friday
Thanksgiving
| Monday 11/27 | Tuesday | Wed | Thurs | Friday
| Monday 12/4 | Tuesday | Wed | Thurs | Friday 12/8